## Sheet1
Detailed Project Work Plan
Tasks | Status | Title | Start date | End date | Duration (in days) | Duration (in %)
Task 1 | Completed | Identify the problems | 2019-09-19 | 2019-09-21 | 2 | 1.111%
Task 2 | Completed | Meeting with sponsor(Board) | 2019-09-22 | 2019-09-22 | 1 | 0.5556%
Task 3 | Completed | Feasibility Study | 2019-09-16 | 2019-09-26 | 9 | 5%
Task 4 | Completed | System Request | 2019-09-26 | 2019-10-01 | 5 | 2.778%
Task 5 | Not Started | Building/Designing the system | 2019-10-20 | 2019-12-20 | 60 | 33.33%
Task 6 | Not Started | Security check | 2019-12-21 | 2020-02-21 | 60 | 33.33%
Task 7 | Not Started | Post Testing and Implementation | 2020-02-22 | 2020-03-19 | 27 | 15%
Total Time |  |  | 2019-09-19 | 2020-03-19 | 180 | 100%
Figure 1.2 Detailed project work Plan